## Automation Review status Issuin
Automation Test Scenario | Test case ID | Review Comments | Reviewed Date | Status | ETA | Closing date | Functional Dry Run Status | Date | Dry Run Comments
TS_PRI_ISS_AccountBoarding | TS_PRI_ISS_001_TC_001 | 30.06.2026: 1. In result Steps Exact Field value need to show in shared results instead of MDM Value name Eg: (${screenname} ${fieldname}). 2. In the downloaded pass logs, the Flow Details section does not display the information from the Design Module with proper line breaks, making the step descriptions difficult to read. 3. Step wise description should be clear with Navigation screen, Field name and value name for Validation/ Verification/ Steps. Note: This point should be addressed in all the test cases. | 30-06-2026 | Open |  |  | Completed | 2nd Aug | For Account boarding, If Customer, Account or Card is not generated. The value already present in MDM should not get removed as empty. Existing data should be present in MDM.
TS_PRI_ISS_001_TC_002
TS_PRI_ISS_001_TC_003
TS_PRI_ISS_001_TC_004
TS_PRI_ISS_001_TC_005
TS_PRI_ISS_AccountMaintenance | TS_PRI_ISS_010_TC_002 | In generated Passlogs Descriptions need to be clear on each steps. Requested dry run to check test step description is clear with Navigation screen, Field name and value name for Validation/ Verification/ Steps. | 2026-07-06 | Open |  |  | Completed | 2nd Aug | Change product functionality is failed, Due to this following Change profile and Change status function is also getting failed. Change Product – Failed Change Profile - Hold Change Status - Hold Note: Above mentioned are individual function. If any function is not executed or failed other following function should not get hold.
TS_PRI_ISS_010_TC_003
TS_PRI_ISS_010_TC_004
TS_PRI_ISS_CardMaintenance | TS_PRI_ISS_012_TC_001 | The downloaded log should be displayed in the same format as the Pass Log, with the header "Pass Logs". It should include the Test Case/Scenario, Expected Result, and Actual Result Note: This should applicable for all the test scenarios/ Test case | 2026-07-12 | Open |  |  | Completed | 2nd Aug | Successfully Completed
TS_PRI_ISS_012_TC_005
TS_PRI_ISS_012_TC_006
TS_PRI_ISS_012_TC_010
TS_PRI_ISS_012_TC_013
TS_PRI_ISS_CustomerMaintenance | TS_PRI_ISS_008_TC_004 | Need to remove or skip multiple screenshots captured for same step Step 2: No Highlighter for 'Domain' Step 8: No Highlighter for 'Institution' Step 25: Selecting of 'ExtensionFields' screenshot not available. Step 35: 'Log off' screenshot not available. In 'Field Name' - Instead of using keywords like txt,tb,btn,dd,etc. provide complete words In 'Step Description' & 'Expected Result' - Instead of Step details, '${screenname} ${fieldname}' is mentioned accross all steps. In 'Actuals' & 'Status Msg' - It is mentioned as 'Success. Element Successfully clicked' - Should have mentioned as what happened exactly. | 2026-07-29 | Open
| TS_PRI_ISS_015_TC_001 | Same as above
TS_PRI_ISS_015_TC_006
TS_PRI_ISS_AccountMaintenance_CreditLimit | TS_PRI_ISS_010_TC_001 | Need to implement all above mentioned comments in this scenario | 2026-07-11 | Open |  |  | Completed | 2nd Aug | Change Credit limit is getting failed at 20th step.
TS_PRI_ISS_CardMaintenance_CardActivation | TS_PRI_ISS_014_TC_001 | Step 2: No Highlighter for 'Domain' Step 8: No Highlighter for 'Institution' Step 17: Selecting of 'ManuallyActivateCard' screenshot not available. Step 23: 'Log off' screenshot not available. | 2026-07-29 | Open |  |  | Completed | 4th Aug | Successfully Completed
TS_PRI_ISS_CardManagement_Replace | TS_PRI_ISS_006_TC_008 | During Renewal- > take action > Selecting Renew option screenshot option is not present in captured log. In captured log, Card activation steps following with renew option is showing. Step description and expected result should be relevant to the log 26.Exact field need to be highlighted | 2026-07-12 | Open
TS_PRI_ISS_004_TC_001
TS_PRI_ISS_FeesAndCharges_CreditAdjustment | TS_PRI_ISS_030_TC_001 | Step 2: No Highlighter for 'Domain' Step 8: No Highlighter for 'Institution' Step 29: No Highlighter for 'Currency' Step 23: 'Log off' screenshot not available. | 29-07-2026 | Open
TS_PRI_ISS_Car dMaintenance_StatusCodes | TS_PRI_ISS_043_TC_002 | 1. From Step #25 (Step 24) to Step #31 (Step 30), the screenshots are repetitive and appear to be identical. The screenshots do not clearly highlight the field where the status has changed, 2. As per the provided logs, all status fields were updated and saved simultaneously in a single operation. However, according to the test case breakdown, each status field should be updated and saved individually, with separate validation for each status change. 3. From Step #53 (Step 52) to Step #58 (Step 57), the screenshots are repetitive and inconsistent. They do not clearly highlight the changes made to the status fields or their updated values, and the fields referenced in the test steps are not visibly identified in the screenshots, making verification difficult. | 29-07-2026 | Open
TS_PRI_ISS_043_TC_003
TS_PRI_ISS_044_TC_001
TS_FIL_DomesticSalesTransactions | TS_FIL_007_TC_002 | 1. Steps by step of preparing visain file and placing in Winscp file path is missing. 2. Vaildating against Visain values matching with posted transaction field value is missing. | 29-07-2026 | Open
TS_FIL_DomesticCashTransactions | TS_FIL_007_TC_004 | 1. #17 Step 16 Wait log check if wait log is necessary in passlog | 30-07-2026 | Open
TS_FIL_InternationalATMTransactions | TS_FIL_007_TC_030 | 1. In Info test case details are not mentioned 2.#17 Step 16 Wait log check if wait log is necessary in passlog | 30-07-2026 | Open
TS_PRI_ISS_AccountMaintenance_StatusCodes | TS_PRI_ISS_037_TC_001 | Step 2: No Highlighter for 'Domain' Step 8: No highlighter for 'institution' No highlighter on Step 22 & from Step 33 to Step 38 & Step 50 , Step 52 to Step 55 Step 62 : Logoff In 'Field Name' - Instead of using keywords like txt,tb,btn,dd,etc. provide complete words In 'Step Description' & 'Expected Result' - Instead of Step details, '${screenname} ${fieldname}' is mentioned accross all steps. In 'Actuals' & 'Status Msg' - It is mentioned as 'Success. Element Successfully clicked' - Should have mentioned as what happened exactly. | 30-07-2026 | Open
TS_PRI_ISS_037_TC_002
TS_PRI_ISS_038_TC_001
TS_PRI_ISS_038_TC_002
TS_PRI_ISS_CardMaintenance | TS_PRI_ISS_008_TC_004 | 1. #16 to #18 Step 15 to 17 Field name "Auth gen" is not found in the prime screen and ATM, Quashi, Cash check box tick was not highlighted. Also as per the screen all the items including above the check box were already ticked 2. #22 to # 24 and Step 21 to Step 23 the screen is mismatched with the exact request as per "Field Name" 3. #24 and Step 23 the screen for uncheck Cash button screen was missing 4. #25 Step 24 to click on save is correct, however as per the previous steps it is requested to uncheck ATM, Quashi, Cash, but while clicking on save button, these items were not unchecked. 5. #28 to #30 and Step 27 to Step 29 the check box not highlighted as per passlog 6. #49 and Step 48 the field was not highlighted in the passlog 7. #60 and Step 59 the field "Manage Address Roles" is missing on the screen shot 8. #61 Step 60 mentioned to Click on AddressRole_Mail_CB_btn, but as per the #62 Step 61 the "Mail" check box was clicked under "Edit Address Roles" which is mismatching 9. #64 and Step 63 it mentioned as Address Roles Mail Checked" which is highlighted in Passlog, but additionally Check box for Mail under "Edit Address Role" was also checked in 10. #71 and Step 70 SetVirtualCard_BTN field is missing on the screenshot 11. #72 and Step 71 as per the request "VirtualCardCheckbox_btn" should be clicked, but on the screenshot check box not clicked 12. #77 and Step 76 the Log off button click page was missing as per screen shot, where as only logged off page appears | 30-07-2026 | Open
TS_PRI_ISS_012_TC_001
TS_PRI_ISS_012_TC_005
TS_PRI_ISS_012_TC_006
TS_PRI_ISS_012_TC_010
TS_PRI_ISS_012_TC_013
TS_PRI_ISS_CardManagement_Renewal | TS_PRI_ISS_004_TC_001 | 17. field need to be highlighted 20. card activation status field need to be highlighted 26. field need to be highlighted Downloaded Flow details info: No data is showing | 2026-03-08 | Open
TS_PRI_ISS_FeesAndCharges_CreditAdjustment | TS_PRI_ISS_030_TC_001 | 10. Step description and expected result should be relevant to the logs for all steps 12. Expected result should be successfully clicked on new batch | 2026-08-04 |  |  |  | Completed | 04-08-2026
TS_PRI_ISS_FeesAndCharges_DebitAdjustment | TS_PRI_ISS_030_TC_002 | Failed at step 25 Expected value--Neo VISA Debit Card--did not match the actual value--VISA Etisalat Signature--in Product_txt field | 2026-08-04 |  |  |  | Completed | 04-08-2026

## Automation Review status Acquir
Automation Test Scenario | Test case ID | Review Comments | Reviewed Date | Notes | Status | Closing date | Functional Dry Run Status | Run Date | Dry Run Comments
TS_MRB_Single_POS | TS_MRB_001_TC_001 | 1. Merchant Account & Location Level Profile Commission & Vat value need to be selected when boarding Merchant 2.Allowed transaction type screen shot need to be included. | 30-06-2026 | 1. Merchant Account & Location Level Profile: Commission & VAT value selection is included in KT session but missing in flow creation. 2. Allowed transaction type included in KT session but missing in flow creation. | Closed | 2026-07-03 | Completed | 04-08-2026
TS_MRB_002_TC_001
TS_MRB_003_TC_001
TS_MRB_017_TC_001
TS_MRB_001_TC_002
TS_MRB_002_TC_002
| TS_MRB_003_TC_002 | 3. In generated Passlogs Descriptions need to be clear on each steps. Requested dry run to check test step description is clear with Field name and value name for Validation/ Verification/ Steps. | 2026-07-04 | 1. In generated Passlogs Descriptions need to be clear on each steps. Requested dry run to check test step description is clear with Field name and value name for Validation/ Verification/ Steps. | Open
TS_MRB_017_TC_002
TS_MRB_017_TC_003
TS_MRB_017_TC_004
| TS_MRB_001_TC_003 | 1. IN step 28:Bank details are captured again under the customer details screen, although they already added earlier in the flow 2. under merchant customer details, statement template is not added 3.The commission posting merthod is not selected in the test flow under the account details section. 4.Payment type not added 1.Under location, commission posting method is not added. 5. Allowed transaction type screen not added
TS_MRB_002_TC_003
TS_MRB_003_TC_003
TS_MRB_003_TC_006
TS_MRB_003_TC_007
TS_MRB_012_TC_001
TS_MRB_Single_Merchant_EditDetails | TS_MRB_001_TC_005 | Same as above | 2026-07-07 |  | Open |  | Completed | 04-08-2026
TS_MRB_002_TC_005
TS_MRB_003_TC_005
TS_MRB_Single_Merchant_Multiple_Account | TS_MRB_004_TC_001 | 1.No Screens for Existing Customer. 2.Need to add the Statement Template 3.need to add the Commission posting method under both Account & Location. 4.Need to Select the Allowed Transaction Type. 5.Allocated Terminal Screen need to add | 31-07-2026 |  | Open |  | Fail | 4-08-2026 | Step 68: Is getting failed when running dry run.
TS_MRB_Single_Merchant_Multiple_Loc | TS_MRB_004_TC_002 | 1.No Screens for Existing Customer. 2.Need to add the Statement Template 3.need to add the Commission posting method under both Account & Location. 4.Need to Select the Allowed Transaction Type. | 31-07-2026 |  | Open
TS_MRB_Single_Merchant_Multiple_Terminal | TS_MRB_004_TC_003 | 1.1st Terminal number input- invalid but finally Number got Generated 2.Created only one terminal but finally 3 Terminal there in Customer Service Screen. | 31-07-2026 |  | Open
TS_MRB_Single_Merchant_GROSS_PROFILE | TS_MRB_005_TC_001 | 1.Main Account Screens Not there. 2.need to add commission posting method under Location. 3.need to select allowed Transaction Type. 4.Need to add Account Routing Reflection Screen. | 31-07-2026 |  | Open
TS_MRB_005_TC_002
TS_MRB_005_TC_003
TS_MRB_Single_Merchant_NET_PROFILE | TS_MRB_006_TC_001 | 1.for net commission Profile single merchant should be onboareded with single Account. | 31-07-2026 |  | Open
TS_MRB_006_TC_004
TS_MRB_SingleLocation_PayType_SWIFT | TS_MRB_007_TC_001 | 1.Need to Select the statement template. 2.need to add commission posting method under Account. 3.need to add commission posting method under Location 4.need to select allowed Transaction Type. 5.Need to add Payment Type -- Swift Reflection Screen. 6.Allocated Terminal Screen need to add | 31-07-2026 |  | Open
TS_MRB_SingleLocation_PayType_ON_US | TS_MRB_007_TC_002 | 1.Need to Select the statement template. 2.need to provide VAT Registration Number. 3.need to add commission posting method under Account. 4.need to add commission posting method under Location 5.need to select allowed Transaction Type. 6.Allocated Terminal Screen need to add 7.Need to add Payment Type -- on-us Reflection Screen. 8.one ERROR Screen is there in last. | 31-07-2026 |  | Open
TS_MRB_SingleLocation_PayCycle_Daily | TS_MRB_007_TC_004 | 1.Need to Select the statement template. 2.need to provide VAT Registration Number. 3.need to add commission posting method under Account. 4.need to add commission posting method under Location - it got skiped(28) 5.need to select allowed Transaction Type. 6.Need to highlight fields(nothing is highlight). 6.Allocated Terminal Screen need to add 7.Need to add Payment Cycle -- Daily Reflection Screen. | 31-07-2026 |  | Open
TS_MRB_SingleLocation_PayCycle_Monthly | TS_MRB_007_TC_005 | 1.Need to Select the statement template. 2.need to add commission posting method under Account. 3.need to add commission posting method under Location - it got skiped(28) 4.need to select allowed Transaction Type. 6.Allocated Terminal Screen need to add | 31-07-2026 |  | Open
TS_MRB_SingleLocation_PayCycle_Weekly | TS_MRB_007_TC_006 | 1.need to add commission posting method under Location 2.Need to add Payment cycle--Weekly Reflection Screen. 3.Allocated Terminal Screen need to add 4.need to select allowed Transaction Type. | 31-07-2026 |  | Open
TS_MRB_Single_Merchant_ECOM | TS_MRB_008_TC_001 | 1.product should be selected as AED Account | 31-07-2026 |  | Open
TS_MRB_008_TC_004
TS_MRB_SingleLocation_PayType_ON_US | TS_MRB_009_TC_001 | 1.institution dropdown screen missing gave showmenu screen instead of institution drop down(Step no -8) 2.Statement template not added(After 15th step) 3.Commission posting method needs to add (after 22nd step) 4.Allowed transaction types screen need to add(after 45th step) 5.Allocated terminal screen nedd to add 6.Paytype-ONUS screen needs to add | 31-07-2026 |  | Open
TS_MRB_Single_Merchant_POS_OFF_US | TS_MRB_009_TC_002 | 1.institution drop down screen replaced with application screen 2.statement template not selected 3.Transaction typeselection screen missed 4.off us payment type not selected only non mashreq bank selected need to select payment type as UAEFTS(after 25th step) 5.Commission posting method need to select 6.Dcc should not be allowed(step no 37) 7.Allowed transaction type Screen need to add ( | 31-07-2026 |  | Open
TS_MRB_009_TC_003
TS_MRB_Single_Merchant_ECOM | TS_MRB_009_TC_012 | 1.institution dropdown screen missing gave showmenu screen instead of institution drop down 2.Allowed transaction types selection screen missed 3.Single merchant ECOMM needs to onboard with AED product | 31-07-2026 |  | Open
TS_MRB_Single_Merchant_ECOM | TS_MRB_010_TC_001 | 1.Not a PF account PF account should be onboarded with two account one is for AED product and other account is AED PF account | 31-07-2026 |  | Open
TS_MRB_010_TC_003
TS_MRB_010_TC_004
TS_MRB_010_TC_005
TS_MRB_010_TC_007
TS_MRB_Single_Merchant_ECOM | TS_MRB_011_TC_001 | 1.Selected AED PF account as a Product PA should be onboaarded with AED product | 31-07-2026 |  | Open
TS_MRB_011_TC_002
TS_MRB_011_TC_003